## Dashboard
AIRBNB PROJECT DASHBOARD
GitHub Project Management Dashboard
Total Tasks | Done | In Progress | Review | Todo | Backlog | Overall Progress | High Priority |  | Done Rate | Due Today | Overdue
30 | 19 | 2 | 7 | 2 | 0 | 87.67% | 23 |  | 63.33% | 0 | 0
Status | Tasks | [7 empty] | Workstream | Tasks
Backlog | 0 | [7 empty] | Project Setup | 4
Todo | 2 | [7 empty] | Data Understanding | 2
In Progress | 2 | [7 empty] | Data Cleaning | 8
Review | 7 | [7 empty] | Database and ERD | 6
Done | 19 | [7 empty] | SQL Analysis | 1
[9 empty] | Python EDA | 1
[9 empty] | Statistics | 1
[9 empty] | Documentation and Presentation | 7
KANBAN BOARD
BACKLOG |  | TODO |  | IN PROGRESS |  | REVIEW |  | DONE
A028 | Insights and recommendations | A023 | Finalize visualizations | A015 | Finalize ERD | A013 | Final cleaned dataset | A001 | Create repository
A029 | Rehearse presentation | A025 | Prepare presentation | A020 | Complete SQL analysis | A019 | Database integrity | A002 | Add members
A030 | Submit final project | A026 | Review repo structure | A021 | Complete Python EDA | A022 | Validate statistics | A003 | Push branches
|  | A027 | Verify contributions | A024 | Finalize README |  |  | A004 | Define objectives
[8 empty] | A005 | Understand fields
[8 empty] | A006 | Data quality check
[8 empty] | A007 | Clean locations
[8 empty] | A008 | Standardize fields
[8 empty] | A009 | Date to month
[8 empty] | A010 | Price numeric
[8 empty] | A011 | Missing ratings
[8 empty] | A012 | Remove duplicates
[8 empty] | A014 | Sketch ER model
[8 empty] | A016 | Create MySQL DB
[8 empty] | A017 | Define SQL types
[8 empty] | A018 | Load data to MySQL
Progress is automatically linked to Status: Backlog 0%, Todo 0%, In Progress 50%, Review 90%, Done 100%. Overall Progress is the average of these status-based percentages. Done Rate shows the percentage of tasks fully completed.

## Kanban Tasks
ID | Task | Workstream | Owner | Status | Priority | Start Date | Target Date | Progress | Notes
A001 | Create GitHub group repository | Project Setup | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-11 | 100% | Repository created
A002 | Add group members to repository | Project Setup | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-11 | 100% | Access confirmed
A003 | Create and push individual branches | Project Setup | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-11 | 100% | Branch commits completed
A004 | Define project objectives and research questions | Data Understanding | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-11 | 100% | Project questions documented
A005 | Understand dataset fields | Data Understanding | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-12 | 100% | Field meanings reviewed
A006 | Inspect missing values and data quality | Data Cleaning | Jan (Program Manager) | Done | High | 2026-08-10 | 2026-08-12 | 100% | Initial quality checks complete
A007 | Clean property location values | Data Cleaning | Jan (Program Manager) | Done | High | 2026-08-11 | 2026-08-12 | 100% | Invalid and special character values removed
A008 | Standardize country and proximity fields | Data Cleaning | Jan (Program Manager) | Done | Medium | 2026-08-11 | 2026-08-12 | 100% | Categories standardized
A009 | Convert date to month | Data Cleaning | Jan (Program Manager) | Done | Medium | 2026-08-11 | 2026-08-12 | 100% | Month feature created
A010 | Convert price to numeric | Data Cleaning | Jan (Program Manager) | Done | High | 2026-08-11 | 2026-08-12 | 100% | Price cleaned for analysis
A011 | Handle missing ratings | Data Cleaning | Jan (Program Manager) | Done | Medium | 2026-08-11 | 2026-08-12 | 100% | Missing ratings treated
A012 | Remove duplicate records | Data Cleaning | Nadiya | Done | High | 2026-08-11 | 2026-08-12 | 100% | Duplicates removed
A013 | Export final cleaned dataset | Data Cleaning | Nadiya | Done | High | 2026-08-12 | 2026-08-12 | 100% | Final validation before lock
A014 | Sketch Entity Relationship Model | Database and ERD | Nadiya | Done | High | 2026-08-12 | 2026-08-11 | 100% | Initial relational design completed
A015 | Finalize Entity Relationship Diagram | Database and ERD | Nadiya | Done | High | 2026-08-12 | 2026-08-13 | 100% | Finalize keys and relationships
A016 | Create Airbnb MySQL database | Database and ERD | Jan (Program Manager) | Done | High | 2026-08-12 | 2026-08-12 | 100% | airbnb_project database working
A017 | Define SQL table data types | Database and ERD | Jan (Program Manager) | Done | High | 2026-08-12 | 2026-08-12 | 100% | Schema types established
A018 | Load cleaned data into MySQL | Database and ERD | Jan (Program Manager) | Done | Critical | 2026-08-12 | 2026-08-12 | 100% | Cleaned data loaded
A019 | Validate row counts and database integrity | Database and ERD | Nadiya | Review | High | 2026-08-12 | 2026-08-13 | 90% | Cross check database against cleaned file
A020 | Complete core SQL analysis | SQL Analysis | Jan (Program Manager) | Review | High | 2026-08-12 | 2026-08-14 | 90% | Complete remaining analytical queries
A021 | Complete Python exploratory analysis | Python EDA | Jan (Program Manager) | In Progress | High | 2026-08-12 | 2026-08-14 | 50% | Finalize EDA and outputs
A022 | Validate statistical tests | Statistics | Nadiya | Review | High | 2026-08-12 | 2026-08-14 | 90% | Review test assumptions and interpretation
A023 | Finalize project visualizations | Documentation and Presentation | Jan (Program Manager) | Review | High | 2026-08-12 | 2026-08-14 | 90% | Select final charts for presentation
A024 | Finalize README documentation | Documentation and Presentation | Nadiya | Review | Medium | 2026-08-13 | 2026-08-14 | 90% | Document workflow, findings and methodology
A025 | Prepare final presentation | Documentation and Presentation | Jan (Program Manager) | Done | High | 2026-08-13 | 2026-08-14 | 100% | Build concise project story
A026 | Review GitHub repository structure | Documentation and Presentation | Jan (Program Manager) | Review | Medium | 2026-08-13 | 2026-08-14 | 90% | Check notebooks, scripts, figures and slides
A027 | Verify all member contributions | Project Setup | Jan (Program Manager) | Review | High | 2026-08-13 | 2026-08-14 | 90% | Confirm member commits and branches
A028 | Prepare project insights and recommendations | Documentation and Presentation | Nadiya | In Progress | Medium | 2026-08-13 | 2026-08-14 | 50% | Translate findings into recommendations
A029 | Rehearse final presentation | Documentation and Presentation | Jan (Program Manager) | Todo | Medium | 2026-08-13 | 2026-08-14 | 0% | Check timing and speaking roles
A030 | Submit final project | Documentation and Presentation | Jan (Program Manager) | Todo | Critical | 2026-08-14 | 2026-08-14 | 0% | Final submission milestone
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Lists
Status | Priority | Workstream | Owner | Status | Progress
Backlog | Low | Project Setup | Jan (Program Manager) | Backlog | 0%
Todo | Medium | Data Understanding | Nadiya | Todo | 0%
In Progress | High | Data Cleaning | Berta | In Progress | 50%
Review | Critical | Database and ERD |  | Review | 90%
Done |  | SQL Analysis | Member 4 | Done | 100%
Python EDA
Statistics
Documentation and Presentation